## Test cases
Test case # | Test type | Test steps | Task & problems | Expected result | Output result | Severity | Status | Remark/Note
BCM
1 | Document | other document | add/upload document using browse | while choose file there should show file name | still showing choose file | medium | pass | need to fix!
2 | vendor | received date | update file | while choose file there should show file name | still showing choose file | medium | pass | need to fix!
3 | legal and tech | technical details | delete valuation | delete success | it shows [error object] | High | fail | need to fix! but when we change tab and rechange to it the valuation is deleted
3.1 | legal and tech | technical details | add file | save success | saved successfully | high | fail | need to fix! file saved success even without any details
4 | verification | Residence verification (family details) | delete member | delete success | it shows [error object] | High | fail | need to fix! but when we change tab and rechange to it the member deleted
5 | MOF | send SMS | Payment gateway send sms | sms send success and received successfully | sms didn't received | high | fail | In web it shows SMS sent success
SCM
1 | verification | residence verification | upload file | shouldn't done | file inserted successfully | high | fail
2 | Mof | Payment history | Click view | only view option option and close | it shows [error object] and save button | high | fail
CRO
1 | verification | residence verification | upload file | shouldn't done | file inserted successfully | high | fail
2 | Mof | Payment history | Click view | only view option option and close | it shows [error object] | high | fail | save button and we can edit UTR no.
CEO
1 | verification | residence verification | upload file | shouldn't done | file inserted successfully | high | fail
2 | final calc | insurance | try to edit info | only view | we can edit and save the changes | high | fail
Branch QC
1 | Lod | name of document | delete valuation | delete success | it shows [error object] | High | fail | need to fix! but when we change tab and rechange to it the valuation is deleted
2 | Mof | Payment history | Click view | only view option option and close | it shows [error object] | high | fail | save button and we can edit UTR no.
Central OPS
1 | verification Tab | Residence verification | residence images try to upload images | shouldn't done | file inserted successfully | high | fail
2 | Lod | try Upload document | we can add,update,delete document | Should be freeze | Add successfully | high | fail
3 | final calc | Final scheme | Change disbursed date | Should be freeze | we can change but cant't save it | low | pass
4 | Mof | Payment history | Click view | only view option option and close | it shows [error object] | high | fail | save button and we can edit UTR no.

## Description
Sr No | Module | Issues
1 | BCM | 6
2 | SCM | 2
3 | CRO | 2
4 | CEO | 2
5 | Branch QC | 2
6 | Central OPS | 4
| Total | 18